## 2G
Functionality Acceptance Test Procedure
Radio Technology LTE
Version : 001.02 / Revision Date: 04/12/2015
Project Name |  | : | RAN Swap Jabo 2025 - 8639 |  |  |  |  | This test form has been approved for use in the ATP Functionality EnodeB LTE Network Indosat by:
Vendor Name |  | : | Huawei
Number PO |  | : | 4810016207
Scope Of Work |  | : | 2T2R L900_(10)+4T4R L1800_(30)+4T4R L2100_(25)+HOS1
Date/Time |  | : | 2025-08-01 |  |  |  |  | INDOSAT |  |  |  |  | VENDOR
[8 empty] | NETWORK DESIGN & DEPLOYMENT |  |  |  |  | ERICSSON
Site Name / Site Id |  | : | KUNCIRAN_INDAH_BL / 11TGR0278 / 11TGR0278_FUSI_SWP_Q2EX |  |  |  |  | Reymond Renaldy (Div. PQA) |  |  |  |  | Aminuddin Fauzan
Address |  | : | JL. BOULEVARD GRAHA RAYA
GPS Coordinate (Lat/Lon) |  | : | -6.22923 / 106.68309 |  |  |  |  | NETWORK OPERATION |  |  |  |  | HUAWEI
[8 empty] | Iin Sri Astuti (Div. Access Operation) |  |  |  |  | Cheyagang
PIC Indosat /Hp: |  | :
PIC Vendor/Hp: |  | : | Dipo Swarna Arya Putra/0856-9363-4099 |  |  |  |  | NETWORK ARCHITECTURE SOLUTION & OPTIMIZATION |  |  |  |  | NOKIA
MSISDN Number (A#/B#) |  |  | 85715324355
[8 empty] | Joko Riswadi (Div. Network Optimization) |  |  |  |  | Agus Kelana
Video Capture FileName (Cell-Sector1/Cell-Sector2/Cell-Sector3) :
No. | Item Test | Sector# | MIMO Enable | LAC | BSC ID | Cell Id | BCCH |  | Target Value |  | Achieve Value | Test Result | VideoCapture¦FramePosition (mm.ss.msmsms-mm.ss.msmsms) | Remarks
1 | MSISDN Information
| 1.1 MSISDN Number | 1 | No | 3818 |  | 51201 | 78 |  | MSISDN Number Info |  | 85715324355 | OK
| 1.2 MSISDN Number | 2 | No | 3818 |  | 51202 | 80 |  | MSISDN Number Info |  | 85715324355 | OK
| 1.3 MSISDN Number | 3 | No | 3818 |  | 51203 | 83 |  | MSISDN Number Info |  | 85715324355 | OK
2 | BandWidth, Channel Frequency & CA-Configuration Check
| 2.1 Band Frequency | 1 | No | 3818 |  | 51201 | 78 |  | Refer To NDB |  | G900 | OK | 00:00:52.000-00:01:02.000
| 2.2 Arfcn (BCCH) | 1 | No | 3818 |  | 51201 | 78 |  | Refer To NDB |  | 78 | OK
| 2.3 TCH | 1 | No | 3818 |  | 51201 | 78 |  | Refer To NDB |  | G900 | OK
| 2.4 Band Frequency | 2 | No | 3818 |  | 51202 | 80 |  | Refer To NDB |  | G900 | OK | 00:00:51.000-00:01:01.000
| 2.5 Arfcn (BCCH) | 2 | No | 3818 |  | 51202 | 80 |  | Refer To NDB |  | 80 | OK
| 2.6 TCH | 2 | No | 3818 |  | 51202 | 80 |  | Refer To NDB |  | G900 | OK
| 2.7 Band Frequency | 3 | No | 3818 |  | 51203 | 83 |  | Refer To NDB |  | G900 | OK | 00:00:50.000-00:01:02.000
| 2.8 Arfcn (BCCH) | 3 | No | 3818 |  | 51203 | 83 |  | Refer To NDB |  | 83 | OK
| 2.9 TCH | 3 | No | 3818 |  | 51203 | 83 |  | Refer To NDB |  | G900 | OK
3 | Ping Test 32Byte | [7 empty] | G900 | MIMO 4x4 15MHz
| 3.1 Ping 32Byte | 1 | No | 3818 |  | 51201 | 78 |  | <= 350 ms | 28 s | 210.8 ms | Ok |  | 5 Attempts
| 3.2 Ping 32Byte | 2 | No | 3818 |  | 51202 | 80 |  | <= 350 ms | 22 ms | 58.0 ms | Ok |  | 5 Attempts
| 3.3 Ping 32Byte | 3 | No | 3818 |  | 51203 | 83 |  | <= 350 ms | 36 ms | 60.8 ms | Ok |  | 5 Attempts
4 | Outgoing SMS & Incoming SMS (Short Messaging Service)
| 4.1 SMS Sent & Receive (MSISDN B# = MSISDN A#) | 1 | No | 3818 |  | 51201 | 78 |  | Success |  | Success | OK | 00:01:47.000-00:01:52.000 | 5 Attempts
| 4.2 SMS Sent & Receive (MSISDN B# = MSISDN A#) | 2 | No | 3818 |  | 51202 | 80 |  | Success |  | Success | OK |  | 5 Attempts
| 4.3 SMS Sent & Receive (MSISDN B# = MSISDN A#) | 3 | No | 3818 |  | 51203 | 83 |  | Success |  | Success | OK |  | 5 Attempts
5 | Idle Mode (Verify Cross Sector Check)
| 5.1 Mobility G900 | Mobility | No | 3818 | Mobility | Mobility | Mobility |  | Success |  | Success | OK
| 5.2 Mobility D1800 | Mobility | No | N/A | Mobility | N/A | N/A |  | N/A |  | N/A | N/A
6 | Handover Test
| 6.1 Handover HW to EID | Mobility | No | N/A | Mobility | Mobility | Mobility |  | Success |  | Success | OK
| 6.2 Handover EID to HW | Mobility | No | N/A | Mobility | Mobility | Mobility |  | Success |  | Success | OK
| 6.3 Handover HW to HW | Mobility | No | N/A | Mobility | Mobility | Mobility |  | Success |  | Success | OK
3 | Ping Test 32Byte
4 | Outgoing SMS
4.1 | Incoming SMS
My IM3/BIMA 3
Sector 2
Sector 1
Sector 1
Sector 2
Sector 3
Sector 1
Sector 3
Sector 1
Sector 2
Sector 3
Sector 3
Sector 2

## 4G
Functionality Acceptance Test Procedure
Radio Technology LTE
Version : 001.02 / Revision Date: 04/12/2015
Project Name |  | : | RAN Swap Jabo 2025 - 8639 |  |  |  |  | This test form has been approved for use in the ATP Functionality EnodeB LTE Network Indosat by:
Vendor Name |  | : | Huawei
Number PO |  | : | 4810016207
Scope Of Work |  | : | 2T2R L900_(10)+4T4R L1800_(30)+4T4R L2100_(25)+HOS1
Date/Time |  | : | 2025-08-01 |  |  |  |  | INDOSAT |  |  |  |  | VENDOR
[8 empty] | NETWORK DESIGN & DEPLOYMENT |  |  |  |  | ERICSSON
Site Name / Site Id |  | : | KUNCIRAN_INDAH_BL / 11TGR0278 / 11TGR0278_FUSI_SWP_Q2EX |  |  |  |  | Reymond Renaldy (Div. PQA) |  |  |  |  | Aminuddin Fauzan
Address |  | : | JL. BOULEVARD GRAHA RAYA
GPS Coordinate (Lat/Lon) |  | : | -6.22923 / 106.68309 |  |  |  |  | NETWORK OPERATION |  |  |  |  | HUAWEI
[8 empty] | Iin Sri Astuti (Div. Access Operation) |  |  |  |  | Cheyagang
PIC Indosat /Hp: |  | :
PIC Vendor/Hp: |  | : | Dipo Swarna Arya Putra/0856-9363-4099 |  |  |  |  | NETWORK ARCHITECTURE SOLUTION & OPTIMIZATION |  |  |  |  | NOKIA
MSISDN Number (A#/B#) |  |  | 85715324355
[8 empty] | Joko Riswadi (Div. Network Optimization) |  |  |  |  | Agus Kelana
Video Capture FileName (Cell-Sector1/Cell-Sector2/Cell-Sector3) :
No. | Item Test | Sector# | MIMO Enable | TAC/LAC | EnodeBId/RNCId | Cell Id | PCI |  | Target Value |  | Achieve Value | Test Result | VideoCapture¦FramePosition (mm.ss.msmsms-mm.ss.msmsms) | Remarks
1 | MSISDN Information
| 1.1 MSISDN Number | 1 | Yes | 32413 | 313815 | 71 | 357 |  | MSISDN Number Info |  | 85715324355 | OK
| 1.2 MSISDN Number | 2 | Yes | 32413 | 313815 | 73 | 359 |  | MSISDN Number Info |  | 85715324355 | OK
| 1.3 MSISDN Number | 3 | Yes | 32413 | 313815 | 72 | 358 |  | MSISDN Number Info |  | 85715324355 | OK
2 | BandWidth, Channel Frequency & CA-Configuration Check
| 2.1 BandWidth | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Refer To NDB |  | 20 MHz | OK | 00:00:52.000-00:01:02.000
| 2.2 Earfcn DownLink (DL) /UpLink (UL) | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Refer To NDB |  | 1625 / 19625 | OK
| 2.3 PCI | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Refer To NDB |  | 357 | OK
| 2.4 Carrier Aggregation / CA-Configuration | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Refer To NDB |  | Active | OK
| 2.5 BandWidth | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Refer To NDB |  | 20 MHz | OK | 00:00:51.000-00:01:01.000
| 2.6 Earfcn DownLink (DL) /UpLink (UL) | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Refer To NDB |  | 1625 / 19625 | OK
| 2.7 PCI | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Refer To NDB |  | 359 | OK
| 2.8 Carrier Aggregation / CA-Configuration | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Refer To NDB |  | Active | OK
| 2.9 BandWidth | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Refer To NDB |  | 20 MHz | OK | 00:00:50.000-00:01:02.000
| 2.10 Earfcn DownLink (DL) /UpLink (UL) | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Refer To NDB |  | 1625 / 19625 | OK
| 2.11 PCI | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Refer To NDB |  | 358 | OK
| 2.12 Carrier Aggregation / CA-Configuration | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Refer To NDB |  | Active | OK
3 | DL/UL Speedtest Ookla (Isat & 3) & Ping Test 32Byte | [7 empty] | LTE | MIMO 4x4 15MHz
| 3.1. Throughput Downlink | 1 | Yes | 32413 | 313815 | 71 | 357 |  | DL => 30 Mbps | 16.94 Mbps | 50.6 Mbps | OK | 00:01:37.000-00:01:41.000 | 5 Attempt
| 3.2. Throughput Uplink | 1 | Yes | 32413 | 313815 | 71 | 357 |  | UL => 11 Mbps | 6.66 Mbps | 40.7 Mbps | OK |  | 5 Attempt
| 3.3. Ping Test 32Byte | 1 | Yes | 32413 | 313815 | 71 | 357 |  | <= 60 ms | 28 s | 30.0 ms | OK |  | 5 Attempt
| 3.4. Throughput Downlink | 2 | Yes | 32413 | 313815 | 73 | 359 |  | DL => 30 Mbps | 16.37 Mbps | 56.9 Mbps | OK | 00:01:37.000-00:01:41.000 | 5 Attempt
| 3.5. Throughput Uplink | 2 | Yes | 32413 | 313815 | 73 | 359 |  | UL => 11 Mbps | 6.64 bps | 43.7 Mbps | OK |  | 5 Attempt
| 3.6. Ping Test 32Byte | 2 | Yes | 32413 | 313815 | 73 | 359 |  | <= 60 ms | 22 ms | 15.0 ms | OK |  | 5 Attempt
| 3.7. Throughput Downlink | 3 | Yes | 32413 | 313815 | 72 | 358 |  | DL => 30 Mbps | 16.34 Mbps | 72.9 Mbps | OK | 00:01:39.000-00:01:43.000 | 5 Attempt
| 3.8. Throughput Uplink | 3 | Yes | 32413 | 313815 | 72 | 358 |  | UL => 11 Mbps | 4.53 Mbps | 44.8 Mbps | OK |  | 5 Attempt
| 3.9. Ping Test 32Byte | 3 | Yes | 32413 | 313815 | 72 | 358 |  | <= 60 ms | 36 ms | 16.0 ms | OK |  | 5 Attempt
4 | Ping Test 32Byte | [7 empty] | LTE | MIMO 4x4 15MHz
| 4.1 Ping 32Byte | 1 | Yes | 32413 | 313815 | 71 | 357 |  | <= 60 ms | 28 s | 55.4 ms | OK |  | 5 Attempts
| 4.2 Ping 32Byte | 2 | Yes | 32413 | 313815 | 73 | 359 |  | <= 60 ms | 22 ms | 51.2 ms | OK |  | 5 Attempts
| 4.3 Ping 32Byte | 3 | Yes | 32413 | 313815 | 72 | 358 |  | <= 60 ms | 36 ms | 50.2 ms | OK |  | 5 Attempts
5 | Outgoing SMS & Incoming SMS (Short Messaging Service)
| 5.1 SMS Sent & Receive (MSISDN B# = MSISDN A#) | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK | 00:01:47.000-00:01:52.000 | 5 Attempts
| 5.2 SMS Sent & Receive (MSISDN B# = MSISDN A#) | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK |  | 5 Attempts
| 5.3 SMS Sent & Receive (MSISDN B# = MSISDN A#) | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK |  | 5 Attempts
6 | CSFB-MOC Test & Fast Return
| 6.1 Cell Re-sellection 4G-2G (MOC Call Setup) | 1 | Yes | 3818 | 3681 | 51201 | - |  | Success |  | Success | OK | 00:01:58.000-00:02:03.000 | 5 Attempts
| 6.2 Voice - Mobile Originating Call (MOC) | 1 | Yes | 3818 | 3681 | 51201 | - |  | Success |  | Success | OK | 00:02:04.000-00:02:19.000 | 5 Attempts
| 6.3 Cell Re-sellection 2G-4G (MOC Call Release) | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK | 00:02:20.000-00:02:21.000 | 5 Attempts
| 6.4 Voice - Mobile Terminating Call (MTC) | 1 | Yes | 3818 | 3681 | 51201 | - |  | Success |  | Success | OK | 00:02:59.000-00:03:14.000 | 5 Attempts
| 6.5 Cell Re-sellection 4G-2G (MOC Call Setup) | 2 | Yes | 3818 | 3681 | 51202 | - |  | Success |  | Success | OK | 00:01:56.000-00:02:02.000 | 5 Attempts
| 6.6 Voice - Mobile Originating Call (MOC) | 2 | Yes | 3818 | 3681 | 51202 | - |  | Success |  | Success | OK | 00:02:02.000-00:02:18.000 | 5 Attempts
| 6.7 Cell Re-sellection 2G-4G (MOC Call Release) | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK | 00:02:19.000-00:02:20.000 | 5 Attempts
| 6.8 Voice - Mobile Terminating Call (MTC) | 2 | Yes | 3818 | 3681 | 51202 | - |  | Success |  | Success | OK | 00:02:58.000-00:03:15.000 | 5 Attempts
| 6.9 Cell Re-sellection 4G-2G (MOC Call Setup) | 3 | Yes | 3818 | 3681 | 51203 | - |  | Success |  | Success | OK | 00:02:00.000-00:02:06.000 | 5 Attempts
| 6.10 Voice - Mobile Originating Call (MOC) | 3 | Yes | 3818 | 3681 | 51203 | - |  | Success |  | Success | OK | 00:02:07.000-00:02:22.000 | 5 Attempts
| 6.11 Cell Re-sellection 2G-4G (MOC Call Release) | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK | 00:02:23.000-00:02:24.000 | 5 Attempts
| 6.12 Voice - Mobile Terminating Call (MTC) | 3 | Yes | 3818 | 3681 | 51203 | - |  | Success |  | Success | OK | 00:03:01.000-00:03:16.000 | 5 Attempts
7 | CSFB-MTC Test
| 7.1 LTE - LTE | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK |  | 5 Attempts
| 7.2 LTE - GSM (With CSFB-MTC) | 1 | Yes | 3818 | 3681 | 51201 | - |  | Success |  | Success | OK | 00:02:33.000-00:03:27.000 | 5 Attempts
| 7.3 GSM - LTE (With CSFB-MTC) | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK |  | 5 Attempts
| 7.4 LTE - LTE | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK |  | 5 Attempts
| 7.5 LTE - GSM (With CSFB-MTC) | 2 | Yes | 3818 | 3681 | 51202 | - |  | Success |  | Success | OK | 00:02:32.000-00:03:27.000 | 5 Attempts
| 7.6 GSM - LTE (With CSFB-MTC) | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK |  | 5 Attempts
| 7.7 LTE - LTE | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK |  | 5 Attempts
| 7.8 LTE - GSM (With CSFB-MTC) | 3 | Yes | 3818 | 3681 | 51203 | - |  | Success |  | Success | OK | 00:02:34.000-00:03:29.000 | 5 Attempts
| 7.9 GSM - LTE (With CSFB-MTC) | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK |  | 5 Attempts
8 | VOLTE-MOC Test - LTE (MOC)
| 8.1 LTE-LTE | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK |  | 5 Attempts
| 8.2 LTE-LTE | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK |  | 5 Attempts
| 8.3 LTE-LTE | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK |  | 5 Attempts
9 | VOLTE-MTC Test - LTE (MTC)
| 9.1 LTE-LTE | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK |  | 5 Attempts
| 9.2 LTE-LTE | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK |  | 5 Attempts
| 9.3 LTE-LTE | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK |  | 5 Attempts
10 | Youtube Experience
| 10.1 Acces Aps YouTube | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK |  | 5 Attempts
| 10.2 Acces Aps YouTube | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK |  | 5 Attempts
| 10.3 Acces Aps YouTube | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK |  | 5 Attempts
11 | Social Media Facebook Experience
| 11.1 Acces Social Media Facebook | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK |  | 5 Attempts
| 11.2 Acces Social Media Facebook | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK |  | 5 Attempts
| 11.3 Acces Social Media Facebook | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK |  | 5 Attempts
12 | WhatsApp & WhatsApp Video Call
| 12.1 Whatsapp & Whatsapp Video Call | 1 | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK |  | 5 Attempts
| 12.2 Whatsapp & Whatsapp Video Call | 2 | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK |  | 5 Attempts
| 12.3 Whatsapp & Whatsapp Video Call | 3 | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK |  | 5 Attempts
13 | Idle Mode (Verify Cross Sector Check)
| 13.1 Mobility L900 | Mobility | Yes | 32413 | 313815 | Mobility | Mobility |  | Success |  | Success | OK
| 13.2 Mobility L1800 | Mobility | Yes | 32413 | 313815 | Mobility | Mobility |  | Success |  | Success | OK
| 13.3 Mobility L2100 | Mobility | Yes | 32413 | 313815 | Mobility | Mobility |  | Success |  | Success | OK
14 | Handover Test
| 14.1 Handover HW to EID | Mobility | Yes | 32413 | 313815 | 71 | 357 |  | Success |  | Success | OK
| 14.2 Handover EID to HW | Mobility | Yes | 32413 | 313815 | 73 | 359 |  | Success |  | Success | OK
| 14.3 Handover HW to HW | Mobility | Yes | 32413 | 313815 | 72 | 358 |  | Success |  | Success | OK
3 | DL/UL Speedtest Ookla (Isat & 3)
4 | Ping Test 32Byte
5 | Outgoing SMS
5.1 | Incoming SMS
6 | CSFB-MOC Test & Fast Return
7 | CSFB-MTC Test
8 | VOLTE-MOC Test
9 | VOLTE-MTC Test
10 | Youtube Experience
11 | Social Media Facebook Experience
12 | Whatsapp & Whatsapp Video Call
13 | My IM3/BIMA 3
Sector 2
Sector 3
Sector 1
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 1
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 2
Sector 3
Sector 3
Sector 1
Sector 2
Sector 3

## 5G (hidden)
Functionality Acceptance Test Procedure
Radio Technology LTE
Version : 001.02 / Revision Date: 04/12/2015
Project Name |  | : | SWAP |  |  |  |  | This test form has been approved for use in the ATP Functionality EnodeB LTE Network Indosat by:
Vendor Name |  | : | Huawei
Scope Of Work |  | : | 2T2R L900_(10)+4T4R L1800_(30)+4T4R L2100_(25)+HOS1
Date/Time |  | : | 2025-08-01 |  |  |  |  | INDOSAT |  |  |  |  | VENDOR
[8 empty] | NETWORK DESIGN & DEPLOYMENT |  |  |  |  | ERICSSON
Site Name / Site Id |  | : | KUNCIRAN_INDAH_BL / 11TGR0278 / 11TGR0278_FUSI_SWP_Q2EX |  |  |  |  | Reymond Renaldy (Div. PQA) |  |  |  |  | Aminuddin Fauzan
Address |  | : | JL. BOULEVARD GRAHA RAYA
GPS Coordinate (Lat/Lon) |  | : | -6.22923 / 106.68309 |  |  |  |  | NETWORK OPERATION |  |  |  |  | HUAWEI
[8 empty] | Iin Sri Astuti (Div. Access Operation) |  |  |  |  | Cheyagang
PIC Indosat /Hp: |  | :
PIC Vendor/Hp: |  | : | Gerry / 085778024242 |  |  |  |  | NETWORK ARCHITECTURE SOLUTION & OPTIMIZATION |  |  |  |  | NOKIA
MSISDN Number (A#/B#) |  | : | 85715324355
Joko Riswadi (Div. Network Optimization)
Video Capture FileName (Cell-Sector1/Cell-Sector2/Cell-Sector3) :
No. | Item Test | Sector# | MIMO Enable | TAC/LAC | EnodeBId/RNCId | Cell Id | PCI |  | Target Value |  | Achieve Value | Test Result | VideoCapture¦FramePosition (mm.ss.msmsms-mm.ss.msmsms) | Remarks
1 | MSISDN Information
| 1.1 MSISDN Number | 1 | Yes | 32413 | 313815 | 71 | 114 |  | MSISDN Number Info |  | 85715324355 | OK
| 1.2 MSISDN Number | 2 | Yes | 32413 | 313815 | 72 | 115 |  | MSISDN Number Info |  | 85715324355 | OK
| 1.3 MSISDN Number | 3 | Yes | 32413 | 313815 | 73 | 116 |  | MSISDN Number Info |  | 85715324355 | OK
2 | BandWidth, Channel Frequency & CA-Configuration Check
| 2.1 BandWidth | 1 | Yes | 32413 | 313815 | 71 | 114 |  | Refer To NDB |  | 20 MHz | OK | 00:00:52.000-00:01:02.000
| 2.2 Earfcn DownLink (DL) /UpLink (UL) | 1 | Yes | 32413 | 313815 | 71 | 114 |  | Refer To NDB |  | 1625 / 19625 | OK
| 2.3 PCI | 1 | Yes | 32413 | 313815 | 71 | 114 |  | Refer To NDB |  | 114 | OK
| 2.4 Carrier Aggregation / CA-Configuration | 1 | Yes | 32413 | 313815 | 71 | 114 |  | Refer To NDB |  | Active | N/A
| 2.5 BandWidth | 2 | Yes | 32413 | 313815 | 72 | 115 |  | Refer To NDB |  | 20 MHz | OK | 00:00:51.000-00:01:01.000
| 2.6 Earfcn DownLink (DL) /UpLink (UL) | 2 | Yes | 32413 | 313815 | 72 | 115 |  | Refer To NDB |  | 1625 / 19625 | OK
| 2.7 PCI | 2 | Yes | 32413 | 313815 | 72 | 115 |  | Refer To NDB |  | 115 | OK
| 2.8 Carrier Aggregation / CA-Configuration | 2 | Yes | 32413 | 313815 | 72 | 115 |  | Refer To NDB |  | Active | N/A
| 2.9 BandWidth | 3 | Yes | 32413 | 313815 | 73 | 116 |  | Refer To NDB |  | 20 MHz | OK | 00:00:50.000-00:01:02.000
| 2.10 Earfcn DownLink (DL) /UpLink (UL) | 3 | Yes | 32413 | 313815 | 73 | 116 |  | Refer To NDB |  | 1625 / 19625 | OK
| 2.11 PCI | 3 | Yes | 32413 | 313815 | 73 | 116 |  | Refer To NDB |  | 116 | OK
| 2.12 Carrier Aggregation / CA-Configuration | 3 | Yes | 32413 | 313815 | 73 | 116 |  | Refer To NDB |  | Active | N/A
3 | DL/UL Speedtest Ookla (Isat & 3) & Ping Test 32Byte | [7 empty] | 5G | MIMO 4x4 15MHz
| 3.1. Throughput Downlink | 1 | Yes | 32413 | 313815 | 71 | 114 |  | DL => 70 Mbps | 16.94 Mbps | 130 Mbps | OK | 00:01:37.000-00:01:41.000 | 5 Attempt
| 3.2. Throughput Uplink | 1 | Yes | 32413 | 313815 | 71 | 114 |  | UL => 20 Mbps | 6.66 Mbps | 36,3 Mbps | OK |  | 5 Attempt
| 3.3. Ping Test 32Byte | 1 | Yes | 32413 | 313815 | 71 | 114 |  | <= 60 ms | 28 s | 29 ms | OK |  | 5 Attempt
| 3.4. Throughput Downlink | 2 | Yes | 32413 | 313815 | 72 | 115 |  | DL => 70 Mbps | 16.37 Mbps | 116 Mbps | OK | 00:01:37.000-00:01:41.000 | 5 Attempt
| 3.5. Throughput Uplink | 2 | Yes | 32413 | 313815 | 72 | 115 |  | UL => 20 Mbps | 6.64 bps | 41,0 Mbps | OK |  | 5 Attempt
| 3.6. Ping Test 32Byte | 2 | Yes | 32413 | 313815 | 72 | 115 |  | <= 60 ms | 22 ms | 29 ms | OK |  | 5 Attempt
| 3.7. Throughput Downlink | 3 | Yes | 32413 | 313815 | 73 | 116 |  | DL => 70 Mbps | 16.34 Mbps | 12,5 Mbps | OK | 00:01:39.000-00:01:43.000 | 5 Attempt
| 3.8. Throughput Uplink | 3 | Yes | 32413 | 313815 | 73 | 116 |  | UL => 20 Mbps | 4.53 Mbps | 27,5 Mbps | OK |  | 5 Attempt
| 3.9. Ping Test 32Byte | 3 | Yes | 32413 | 313815 | 73 | 116 |  | <= 60 ms | 36 ms | 35 ms | OK |  | 5 Attempt
4 | Ping Test 32Byte | [7 empty] | 5G | MIMO 4x4 15MHz
| 4.1 Ping 32Byte | 1 | Yes | 32413 | 313815 | 71 | 114 |  | <= 60 ms | 28 s | 29 ms | OK |  | 5 Attempts
| 4.2 Ping 32Byte | 2 | Yes | 32413 | 313815 | 72 | 115 |  | <= 60 ms | 22 ms | 29 ms | OK |  | 5 Attempts
| 4.3 Ping 32Byte | 3 | Yes | 32413 | 313815 | 73 | 116 |  | <= 60 ms | 36 ms | 35 ms | OK |  | 5 Attempts
5 | VOLTE-MOC Test - LTE (MOC)
| 5.1 LTE-LTE | 1 | Yes | 32413 | 313815 | 71 | 114 |  | Success |  | Success | OK |  | 5 Attempts
| 5.2 LTE-LTE | 2 | Yes | 32413 | 313815 | 72 | 115 |  | Success |  | Success | OK |  | 5 Attempts
| 5.3 LTE-LTE | 3 | Yes | 32413 | 313815 | 73 | 116 |  | Success |  | Success | OK |  | 5 Attempts
6 | VOLTE-MTC Test - LTE (MTC)
| 6.1 LTE-LTE | 1 | Yes | 32413 | 313815 | 71 | 114 |  | Success |  | Success | OK |  | 5 Attempts
| 6.2 LTE-LTE | 2 | Yes | 32413 | 313815 | 72 | 115 |  | Success |  | Success | OK |  | 5 Attempts
| 6.3 LTE-LTE | 3 | Yes | 32413 | 313815 | 73 | 116 |  | Success |  | Success | OK |  | 5 Attempts
7 | Youtube Experience
| 7.1 Acces Aps YouTube | 1 | Yes | 32413 | 313815 | 71 | 114 |  | Success |  | Success | OK |  | 5 Attempts
| 7.2 Acces Aps YouTube | 2 | Yes | 32413 | 313815 | 72 | 115 |  | Success |  | Success | OK |  | 5 Attempts
| 7.3 Acces Aps YouTube | 3 | Yes | 32413 | 313815 | 73 | 116 |  | Success |  | Success | OK |  | 5 Attempts
8 | Social Media Facebook Experience
| 8.1 Acces Social Media Facebook | 1 | Yes | 32413 | 313815 | 71 | 114 |  | Success |  | Success | OK |  | 5 Attempts
| 8.2 Acces Social Media Facebook | 2 | Yes | 32413 | 313815 | 72 | 115 |  | Success |  | Success | OK |  | 5 Attempts
| 8.3 Acces Social Media Facebook | 3 | Yes | 32413 | 313815 | 73 | 116 |  | Success |  | Success | OK |  | 5 Attempts
9 | Acces Internet Messaging
| 9.1 Whatsapp & Whatsapp Video Call | 1 | Yes | 32413 | 313815 | 71 | 114 |  | Success |  | Success | OK |  | 5 Attempts
| 9.2 Whatsapp & Whatsapp Video Call | 2 | Yes | 32413 | 313815 | 72 | 115 |  | Success |  | Success | OK |  | 5 Attempts
| 9.3 Whatsapp & Whatsapp Video Call | 3 | Yes | 32413 | 313815 | 73 | 116 |  | Success |  | Success | OK |  | 5 Attempts
10 | Idle Mode (Verify Cross Sector Check)
| 10.1 Mobility 5G | Mobility | Yes | 32413 | 313815 | Mobility | Mobility |  | Success |  | Success | OK
3 | DL/UL Speedtest Ookla (Isat & 3)
4 | Ping Test 32Byte
5 | VOLTE-MOC Test
6 | VOLTE-MTC Test
7 | Youtube Experience
8 | Social Media Facebook Experience
9 | Whatsapp & Whatsapp Video Call
My IM3/BIMA 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 3
Sector 1
Sector 2
Sector 3
Sector 1
Sector 2
Sector 3
Sector 2
Sector 1
Sector 2
Sector 3

## DT Idle Mode
G900 | D1800 | L900
Remark : Clear CrossFeeder | Remark : | Remark : Clear CrossFeeder
L1800 | L2100 | 5G
Remark : Clear CrossFeeder | Remark : Clear CrossFeeder | Remark :

## Mobility Handover
2G Handover Test Huawei to Ericsson | 2G Handover Test Ericsson to Huawei | 2G Handover Test Huawei to Huawei
Remark : Surrounding already HW | Remark : Surrounding already HW | Remark : Handover Success
4G Handover Test Huawei to Ericsson | 4G Handover Test Ericsson to Huawei | 4G Handover Test Huawei to Huawei
Remark : Surrounding already HW | Remark : Surrounding already HW | Remark : Handover Success

## Cell Information
SITE_ID | SiteName | CellName | LAC | CI | PCI | Longitude | Latitude | BAND | Ant_Height | Dir | Elec_Tilt | Mech_Tilt | Antenna_Type | SiteType | EARFCN | EnodeBID | SectorID | ANTENNA_TRANSMISSION_MODE | BANDWIDTH_ | ANTENNA_GAIN_DB | HORIZONTAL_BEAMWIDTH_DEG | VERTICAL_BEAMWIDTH_DEG | REGION | MICRO_CLUSTER_SA | ADDRESS | MOD3 | sec | sector
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L18_11 | 32414 | 31747571 | 71 | 106.661 | -6.2514 | 1800 | 29.5 | 30 | 3 | 0 | A19451902V06 | LTE1800 | 1625 | 317475 | 71 | MIMO | 20 | 19 | 64 | 7.8 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 2 | 11 | 1
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L18_12 | 32414 | 31747572 | 70 | 106.661 | -6.2514 | 1800 | 29.5 | 230 | 3 | 0 | A19451902V06 | LTE1800 | 1625 | 317475 | 72 | MIMO | 20 | 19 | 64 | 7.8 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 1 | 12 | 2
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L18_13 | 32414 | 31747573 | 69 | 106.661 | -6.2514 | 1800 | 29.5 | 320 | 3 | 0 | A19451902V06 | LTE1800 | 1625 | 317475 | 73 | MIMO | 20 | 19 | 64 | 7.8 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 0 | 13 | 3
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L18_21 | 32414 | 31747561 | 71 | 106.661 | -6.2514 | 1800 | 29.5 | 30 | 3 | 0 | A19451902V06 | LTE1800 | 1475 | 317475 | 61 | MIMO | 10 | 19 | 64 | 7.8 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 2 | 21 | 1
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L18_22 | 32414 | 31747562 | 70 | 106.661 | -6.2514 | 1800 | 29.5 | 230 | 3 | 0 | A19451902V06 | LTE1800 | 1475 | 317475 | 62 | MIMO | 10 | 19 | 64 | 7.8 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 1 | 22 | 2
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L18_23 | 32414 | 31747563 | 69 | 106.661 | -6.2514 | 1800 | 29.5 | 320 | 3 | 0 | A19451902V06 | LTE1800 | 1475 | 317475 | 63 | MIMO | 10 | 19 | 64 | 7.8 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 0 | 23 | 3
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L21_11 | 32414 | 31747531 | 71 | 106.661 | -6.2514 | 2100 | 29.5 | 30 | 3 | 0 | A19451902V06 | LTE2100 | 75 | 317475 | 31 | MIMO | 15 | 19 | 62 | 7 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 2 | 11 | 1
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L21_12 | 32414 | 31747532 | 70 | 106.661 | -6.2514 | 2100 | 29.5 | 230 | 3 | 0 | A19451902V06 | LTE2100 | 75 | 317475 | 32 | MIMO | 15 | 19 | 62 | 7 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 1 | 12 | 2
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L21_13 | 32414 | 31747533 | 69 | 106.661 | -6.2514 | 2100 | 29.5 | 320 | 3 | 0 | A19451902V06 | LTE2100 | 75 | 317475 | 33 | MIMO | 15 | 19 | 62 | 7 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 0 | 13 | 3
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L21_21 | 32414 | 31747521 | 71 | 106.661 | -6.2514 | 2100 | 29.5 | 30 | 3 | 0 | A19451902V06 | LTE2100 | 200 | 317475 | 21 | MIMO | 10 | 19 | 62 | 7 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 2 | 21 | 1
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L21_22 | 32414 | 31747522 | 70 | 106.661 | -6.2514 | 2100 | 29.5 | 230 | 3 | 0 | A19451902V06 | LTE2100 | 200 | 317475 | 22 | MIMO | 10 | 19 | 62 | 7 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 1 | 22 | 2
11TGX0024 | PAKUALAM_CM_FN | 11TGX0024_PAKUALAM_CM_L21_23 | 32414 | 31747523 | 69 | 106.661 | -6.2514 | 2100 | 29.5 | 320 | 3 | 0 | A19451902V06 | LTE2100 | 200 | 317475 | 23 | MIMO | 10 | 19 | 62 | 7 | OUTER JAKARTA | MC-SERPONG | JL DONGKAL RT 003 / 005 KEL PONDOK JAGUNG TIMUR | 0 | 23 | 3